## index sheet
name of the tester | Nurul Ashfaque Khan
duration of testing | 1 week
test place document | test plan for evaly
name of tests | number of test cases | number of bugs | test cases link | bug report
login | 31 | 3 | #gid=0 | #gid=1610876154
navigation | 34 | 0 | #gid=904335348
cart | 29 | 2 | #gid=2116251930 | #gid=1053097406
profile | 44 | 6 | #gid=356626750 | #gid=1514039160
search products | 22 | 5 | #gid=2013677392 | #gid=1775576257
total | 160 | 16
name | link | bugs
integrating login to product order confirm | #gid=1635149178 | 0
individually integration test | #gid=216075422 | 4

## Sheet12
test case id | precondition | steps to execute | test case description | test case scenario | test case title | expected result | acutal result | status | test comments
| log out | 1. logout the existing account 2. add a product 3. login again | 1. add a product while logged out 2. log in | add a product before login and check the cart
1 |  |  |  |  | 1. check the added product before login | login is required | after login the page is not doing any action | fail | the page is stucked after giving login information when we refresh then the login is performed
2 |  |  |  |  | product should be correct as it was added to cart before login | product should be correct | product details is correct | pass
3 |  |  | add product and place order | add a product and check the cart | check the product details in the cart | product should be correct | product is correct | pass
4 |  |  |  |  | place order to see if the correct product is placed | correct product should be placed | product is correct | pass
5 |  |  |  |  | cancel the product to see if product is cancelled | product should be cancelled | product is cancelled | pass
6 |  |  | search a product 2. select a category / brand 3. add to the cart | go to a product page and select any category to see if the right category product is appearing | go to a product page and select a category | right category product should appear | right category product is appeared | pass
7 |  |  |  | select the product and add to cart to check if the product is added to the cart successfully | add a product to the cart | right product should be added to the cart | product added to the cart | pass
8 |  |  |  | place order to see that the correct product is placed | place the order | the order should be placed with correct product | product is placed with correct information | pass
9 |  |  | sort a product page by price 2. add product 3. go to back page | 1. search a product 2. sort the price by clicking the sort function by price | click the sort function more than one time then add a product to cart | product should be added to cart | product is added | pass
10 |  |  |  | 1. click the sort button than try to go to the back page | click the sort button more than 1 times | the page should go back to the 1st page from where it came from | not going to the back page if we click the sort more than one time | fail | after clicking the sort it create new page every time. so that everytime we click back it go through the created same page that has been created after clicking continuosly
11 |  |  |  | 1. place order and check the product details | check the product details after placement | product should be correct | product is correct | pass
12 |  |  | 1. check the order navigatons | 1. after ordering check the order navigation that it contains the right product or not | check the product details in order navigations to see the product accuracy | product details should be accurate | accurate | pass
13 |  |  |  | 1. cancel the product and check the order details | check the product details in order to see the product accuracy | product details should be accurate | accurate | pass
14 |  |  | 1. in a logged out account add product to cart and click continue to shipping | 1. add product in logged out account and click continue to shipping | add product and click continue to shipping | 1. shouldnt continue to shipping 2. a messege should appear that ''you cant proceed without login'' | 1. didnt continued to shipping 2. no messege appeared | fail
add a product and see the product is same if we change the account
add a product to an account and log out to see if cart has product
15 |  |  |  |  | add product and logout | product should be available to cart . To understand that if the cart has product, the cart will have blue circle that indicates that it has product | product is still available to the cart | pass
16 |  |  |  |  | login to another account | in an another account, the previously selected product shouldnt be there | previously selected product shouldnt be in another account | fail | Because of same device, system recognise the device and doesnot remove the previously logged in products

## integrating product adding to p
test case ID | precondition | steps to execute | test case description | test case scenario | test case title | expected result | actual result | status | comments | bug ID
int_1 | load the login page | 1. login a Id 2. add a product to cart 3. order confirmation 4. cancel order | check all the function together from login to payment and check it is working correctly | check the login funcitonality and verify that system logs in with valid information | check that - login successful with evaly ID | should log in with evaly ID | logged in | pass
[5 empty] | check that- login successful with gmail ID | should log in with gmail ID | logged in | pass
|  |  |  | add product to the cart and check if the product is added in right amount with right price and then confirm | check if the product is added with right quantity | product should be in default quantity which is 1 | product is in default quantity which is 1 | pass
[5 empty] | check if the product is in right price | product should be in right price | product is in right price | pass
[5 empty] | check if the product continues without address | product shouldnt be continue without address | product didnt continue without address | pass
|  |  |  | after confirming the order check the product details, customer details | check the shop details from where you ordered | shop details should be correct | shop details is correct | pass
[5 empty] | check the customer details | customer details should be correct | customer details is correct | pass | ony the picture is defaulted in customer details means its not showing the customers photo
[5 empty] | check the product details | product details should be correct | product details is correct | pass
|  |  |  | cancel order | check the product cancellation time | product cancellation time should be correct | product cancellation time is correct | pass
[5 empty] | after cancelling product, check if the system wants to know the reason of canceling | system should pop up a text box to know what was the reason for cancelling the order | system wanted to know the reason for what the order was cancelled | pass

## login
test id | test case ID | pre-condition | step to execute | test scenario | test case title | expected result | actual result | status | bug ID
Login_01 |  | load page page https://evaly.com.bd/auth/login | 1. auto default page will appear 2. click to login button | test the login page with different test cases and check if the login page access with invalid data
login with different combination of data
| tc_001 |  |  |  | verify with invalid email & invalid password | should not log in | didnt logged in | pass
| tc_002 |  |  |  | verify with invalid email & valid password | should not log in | didnt logged in | pass
| tc_003 |  |  |  | verify with valid email & invalid password | should not log in | didnt logged in | pass
| tc_004 |  |  |  | verify with empty email & empty password | should not log in | didnt logged in | pass
| tc_005 |  |  |  | verify with empty email & invalid password | should not log in | didnt logged in | pass
| tc_006 |  |  |  | verify with empty email & valid password | should not log in | didnt logged in | pass
| tc_007 |  |  |  | verify with invalid email & empty password | should not log in | didnt logged in | pass
| tc_008 |  |  |  | verify with valid email & empty password | should not log in | didnt logged in | pass
| tc_009 |  |  |  | verify with valid email & valid password | should login | logged in | pass
| tc_010 |  |  |  | enter the place holder text as email in email input section & enter the place holder in password section as password | should not log in | didnt logged in | pass
| tc_011 |  |  |  | sign in google | 1. have to add email or select existing email 2. should be log in | loggin in | pass
|  |  |  | fill the form with different cases | sign up with different cases
| tc_012 |  |  |  | 1. do not fill any information & click submit | 1. should not submit | 1. didnt submit any information | pass
| tc_013 |  |  |  | 1. enter only full name & leave all forms and submit | 1. should not submit | 1. didnt submit any information | pass
| tc_014 |  |  |  | 1. enter only email & leave all forms then submit | 1. should not submit | 1. didnt submit any information | pass
| tc_015 |  |  |  | 1. enter email and full name 2. do not give any password | 1. should not submit | 1. didnt submit any information | pass
| tc_016 |  |  |  | 1. enter invalid email address | 1. should not submit | 1. doesnt accept email that has been used for creating account | pass
| tc_017 |  |  |  | 1. use charecter before "@gmail.com" as email | 1. should not submit
| tc_018 |  |  |  | 1. use only "@gmail.com" as email | 1. should not submit
| tc_019 |  |  |  | 1. fill the information with placeholder given in the text boxes | 1. should not submit
| tc_020 |  |  |  | 1. fill all forms with valid infromation | 1. should submit | 1. submitted | pass
[5 empty] | 1. use unregistered email account | 1. should not submit 2. caution messege "invalid email" should appear | 1. submitted but OTP is required 2. No caution messege appeared | fail | lg_1
use password against the password requirements & check if the edge password was accepted by sign in page
| tc_021 |  |  |  | 1. use only space | should not submit | doesnt submit | pass
| tc_022 |  |  |  | 1. use only keywords | should not submit | doesnt submit | pass
| tc_023 |  |  |  | 1. use only numbers | should not submit | doesnt submit | pass
| tc_024 |  |  |  | 1. use only signs | should not submit | doesnt submit | pass
| tc_025 |  |  |  | 1. use only alphabets & number 2. do not use signs | should not submit | doesnt submit | pass
| tc_026 |  |  |  | 1. use only alphabets & sign 2. do not use numbers | should not submit | doesnt submit | pass
| tc_027 |  |  |  | 1. meet the requirement for password & use password less than 8 charecters | should not submit | doesnt submit | pass
1. check if the sign in & sign up button successfully redirect to to sign in and sign up page
| tc_028 |  |  |  | 1. in the login page, click sign up to see if the page redirect to the sign up page | should redirect to the sign up page | redirected to sign up page | pass
| tc_029 |  |  |  | 1. in the sign up page, click sign in to see if the page redirect to the sign in page | should redirect to the sign in page | redirected to sign in page | pass
1. click forget password and check if the OTP comes
| tc_030 |  |  |  | 1. enter valid email & do not enter password 2. click forget password | an OTP should come | 1. NO OTP has come. Neither in email nor messege in given phone no. | pass
[5 empty] | enter a email that has not signed up with evaly account but signed up with google account directly | an OTP should come | no OTP has come | fail | lg_2
1. check the login UI after writing a password. The UI should behave as expected
| tc_031 |  |  |  | in the login page, the password hide/unhide checkbox is reversed like - clicking unhide button it hides the password and clicking hide button it shows the password | 1. hide button should hide password 2. unhide button should unhide password | 1. hide button unhide the passwrod 2. unhide button hides the password | fail | lg_3

## navigation
test case ID | precondition | steps to execute | test case description | test scenario | test case title | expected result | actual result | status
1 | load the homepage | 1. go to home page 2. check the navigations | 1. check the homepage if the page contains the right details | 1. check if the homepage is displaying the right products | 1. check that the popular event is showing in first sections left corner | 1. popular event should be shown | popular events is shown | pass
2 |  |  |  |  | 1. check if the upcoming events is shown in the 1st sections right corner | 1.upcoming events should be shown | 1. upcoming events is shown | pass
3 |  |  |  | check the image slider | check if the image slider slides to right after clicking the slide check box below the banner | image slider should slide to right | image sildes perfectly | pass
4 |  |  |  |  | check if the image slider slides to left after clicking the slide check box below the banner | image slider should slide to left | image sildes perfectly | pass
5 |  |  |  |  | check image slider slide auto after a while | image should slide automatically after sometimes | slider automatically slides after sometimes | pass
6 |  |  |  |  | check if the sliding time is same for each slides | sliding time should be same after sometimes | sliding time is same | pass
7 |  |  |  |  | check after the last slide, the slide go back to the first slide | slide should go back to the first slide after the last slide | slider is goint back to the first slide | pass
8 |  |  |  |  | check after clicking the event it redirect to the product page | after clicking the event it should redirect to the product page | event redirected to the product page | pass
9 |  |  | check the sections divided in the homepage | check the 2nd section | check that if the 2nd section of homepage is showing the ''Deal of the day'' | should show the deal of the day event | showing deal of the day | pass
10 |  |  |  |  | check if the product slider button is sliding the products | product should slide to right | product slides to right | pass
[5 empty] | check the left product sliding button to check if the product slides to left correctly | product should slide to left | product slides to left | pass
11 |  |  |  | check the trending now section, popular product section , COD, B2B, products section | show trending products in trending now section | product should be shown in trending | product is showing to trending | pass
12 |  |  |  |  | click the right slider button and check if the slider slides to the right | product should slide to right | product sliding to right | pass
13 |  |  |  |  | click the left slider button and check if the slider slides to the left | product should slide to left | product sliding to left | pass
14 |  |  | check the ''shop'' navigation | search shop name | check if the shop name appears after searching | shop name should appear | shop name appeared | pass
15 |  |  |  |  | check the charecter if its case sensitive with big and small alphabets | shop name should appear even the alphabet is small or big but it should be right spelling | shop name appeared | pass
16 |  |  |  |  | click search button without entering any keyword | should display all products | all products are displayed | pass
17 |  |  |  |  | after searching, remove the keyword and seach empty | should bring out all the shops | all shop appeared | pass
18 |  |  |  |  | check if the cross button in search works fine after searching something | should cancel and display all shops | search cancelled and displayed all products | pass
19 |  |  |  | click on a shop and check the products available | first check the shop name is ok or not | shop name should be ok | shop name is ok | pass
20 |  |  |  |  | check shops address | shop address should be ok | address is ok | pass
21 |  |  |  | product is displayed to two separete section. One is for category and another one is for products | check all the products name are displaying | product name is ok | product name is ok | pass
22 |  |  |  |  | check if the cart option is beneath the product information | cart option should be displayed | cart option displayed | pass
23 |  |  |  |  | check all the categories to verify that the right product is appearing after clicking the category | products should be displaying according to category | product displayed according to the category | pass
24 |  |  |  |  | click ''all'' category and verify that all products are displaying | all products should be displaying | all products are displaying | pass
25 |  |  |  | check the brands to verify the right product appearing | after clicking brands check the category belong to the brand and displaying the correct product | category should belong to the brand | category belonged to the brand | pass
26 |  |  |  |  | click ''all'' and verify that - all brands will be displayed as we choose category | products should be displayed according to the category | products are displaying according to the category | pass
27 |  |  |  | check the cart - after adding a product from a shop if the product is added to the cart | add a product to cart and check if the product is added to the cart | product should be added to the cart | products are added to the cart | pass
28 |  |  |  |  | check the price | price should be correct | price is correct | pass
29 |  |  |  |  | check the address that has been saved before | address should be correct | address is correct | pass
30 |  |  | click on ''categories'' | in category page - there are all categories. check all the categories | click on every category and check that - page is showing that paricular category's product listing | product listing should come after clicking the category | product listing has displayed | pass
31 |  |  |  | beneath the category section- there is product sections category wise. there are also subcategories under the category. check the products | searcg the category wise product and check - right product is appearing | product should be displayed according to the category or subcategory | product displayed correctly | pass
32 |  |  |  |  | check that - the product belong to the sub-category | product should belong to the sub-category | product displayed correctly | pass
33 |  |  | check ''order'' | check all the functionalities in order page | check test case 1-30 in given link - click here to see test cases about order that has been executed before | check all the test cases | test cases are given in profile functional testing
34 |  |  | check ''delivery address'' | check all the functionalitiese in delivery address | check test cases from 16 - 28 in another test execution

## cart
test ID | pre condition | steps to execute | test case description | test case title | expected result | actual result | status | bug id | comments
| load homepage | 1. load home page 2. add a product to cart |  | check the cart with different test cases
cart_001 |  |  |  | 1. add no product to the cart | 1. cart wont show any product | cart not showing product | pass
cart_002 |  |  |  | 1. add a product and check if the product is added to the cart | 1. product will add to the cart | product added to the cart | pass
cart_003 |  |  |  | 1. select multiple products and check if the product amount is correct | product amount should be correct | product amount is correct | pass
cart_004 |  |  |  | 1. select multiple products and check if the products are correct | products should be correct | products are correct | pass
cart_005 |  |  |  | 1. check if the product price is correct individually | product price should be correct | product price is correct | pass
cart_006 |  |  |  | 1. select multiple products and check if the total price amount in correct | total price should be correct | total price is correct | pass
cart_007 |  |  |  | check if the product is present at the cart after signout then again sign in | product should present after a log out then again login | product is present | pass
cart_008 |  |  | check product increase and decrease button to verify that it increase/decrease correctly | 1. check if the product in the cart increases after clicking plus button | 1. product should increase | product increases | pass
cart_009 |  |  |  | 1. check if the product in the cart decreases after clicking minus button | 1. product should decrease | product decreases | pass
cart_010 |  |  |  | 1. check if the product goes to negative number clicking munus button | 1. quantity will never go in negative | product quantity didnt go negative | pass
cart_011 |  |  |  | 1. check the subtotal is correct after increasing the quantity | 1. subtotal should be correct | subtotal is correct | pass
cart_012 |  |  |  | 1. check the subtotal is correct after decreasing the quantity | 1. subtotal should be correct | subtotal is correct | pass
cart_013 |  |  |  | 1. check if the product removes after clicking remove button | 1. product should remove | product removed | pass
cart_014 |  |  |  | 1. after removing all products the cart should display "cart is empty" | 1. should display the empty messege | displaying empty messege | pass
cart_015 |  |  | check the address | 1. check if the cart continue to payment without giving address | 1. should not continue to payment without address | payment didnt continue without address | pass
check the address functionality
cart_016 |  |  | after product is added to cart check the address form | if any address is not given then show messege "no address found" | should display the no address found messege | messege shown | pass
cart_017 |  |  |  | leave all the form empty and check if the form is submitted | form should not submit | didnt submit | pass
cart_018 |  |  |  | fill the name and rest of form is empty and check submission works | submission should not work | didnt submit | pass
cart_019 |  |  |  | fill number only and check submission works | submission should not work | didnt submit | pass
cart_020 |  |  |  | fill name & number and check if the submission works | submission should not work | didnt submit | pass
cart_021 |  |  | if division is not selected then distric, upozilla will not be selected | submit without filling division | 1. should not submit 2. disctrict, upozilla will not show the place name | 1. didnt submit 2. the places name wasnt displayed | pass
cart_022 |  |  | fill the valid answer | fill all the valid answer in the form | given data will be submitted | information submitted | pass
cart_023 |  |  | select the check box "outside town" and give the inside town information where there is no UNION, | give all the information inside the town and check if the UNION is displayed | Union names should not appear | union name didnt appeared | pass
cart_024 |  |  |  | give all the information inside the town and check if submission accepted without giving UNION | should not continue submission | submission continued | fail | 1 | if we give information of inside town but we selected outside town selection then submission should not continue system should figure out that the address is not outside the town
cart_025 |  |  |  | give the address outside the town and check if the UNION's displaying | UNION names should display | UNION name displayed | pass
cart_026 |  |  | check if we can create address and set default which we want to get ordered | create another address and check if the address is displayed correctly | address should be displayed correctly | address is displayed | pass
cart_027 |  |  |  | check if the created new address is not default | created new address should be in default | new address is default | pass
cart_028 |  |  |  | set default to the new address and check if it is set to default | after clicking it to the default, new address should be default | new address went to default | pass
cart_029 |  |  | add product to cart and log in to another id and check if the selected products still exists | add product to another id | selected products should not remain selected after loging to another ID | products remain to another ID | fail | 2

## profile
test case id | pre condition | steps to execute | test case descreption | test case scenario | test case title | expected result | actual result | status | bug id
profile_001 | 1. load home page first 2. go to profile | 1. load home page 2. click on profile | check "My order" in profile | 1.go to "My order'' & check if the order details you placed 2. check the navigations in order page | 1. click on "'all'' button 2. check the product that has ordered/placed/ confirmed/ displatched/ cancelled is correct | the correct details of product should be displayed like is ordered/delivered / cancelled etc | displaying correctly | pass
profile_002 |  |  |  |  | 1. click on''placed'' order 2. check if the product has placed is correctly displaying | placed order should display correctly | displaying correctly | pass
profile_003 |  |  |  |  | 1. click on ''confirm'' 2. check, after the confirmation of order , the product is correctly displayed | product confirmation should display if the product is confirmed | displaying correctly | pass
profile_004 |  |  |  |  | 1. click on ''dispatched'' 2. check if the product details is displayed after a successfull delivery | if the product is delivered then it should display | displaying correctly | pass
profile_005 |  |  |  |  | 1. click on ''cancel'' 2. check the product is cancelled & displyed correctly | after cancellation the product should display the cancellation details | displaying correctly | pass
profile_006 |  |  |  | 1. check the ordered product details | 1. check if the product code is appeared | product code should appear | product code appeared | pass
profile_007 |  |  |  |  | 1. check the product details is correct | product details should correct | product details is correct | pass
profile_008 |  |  |  |  | 1. check the product type like, is it cancelled/ delivered | product type should correct | product type is correct | pass
profile_009 |  |  |  |  | 1. check the payment method, like is it going to be ''cash on delivery'' or ''online payment'' | payment method should be displayed | payment method is displayed | pass
profile_010 |  |  |  |  | 1. check the shop name from the product is ordered | shopname should be displayed | shopname is displaying | pass
profile_011 |  |  |  |  | 1. check the customer details is correct or not | customer details should be displayed correctly | customer details is displaying | pass
profile_012 |  |  |  |  | 1. check the product details that has been ordered | ordered product details should be correct | ordered product details is correct | pass
profile_013 |  |  |  |  | 1. check the product price | product price should be same as it was displayed before | product price is same as it was before the order | pass
[5 empty] | check if the client picture appears in the details | 1. customer picture should match to high profile picture | 1. customer picture didnt match to the profile picture inface there is a default picture showing | fail | 1
profile_014 |  |  |  | check the timeline of the product if the order is cancelled | 1. check the product cancellation time | product cancellation time should be correct 2. the time should be international 3. the time should not be local (pc time) | 1. time is ok 2. time was shown according to my computer time while computer time could be wrong | fail | 2
profile_015 |  |  |  |  | 1. beneath the time, check the name of the customer | name of the customer should be perfect | name of the customer is ok | pass
profile_016 |  |  |  |  | 1. check the cancellation reason | cancellation reason should be correct as it was given by the client | cancellation reason is ok | pass
profile_017 |  |  |  |  | 1. In this section, check the products details like if the product is delivered / cancelled / confirmed 2. also the payment details like is it unpaid/paid. | the product details should be correct | product details is correctly displaying | pass
profile_018 |  |  |  | check Order report issues | 1. click ''report issue'' and check that if the report section pop up or not | new pop should come after clicking | new pop up is displayed | pass
profile_019 |  |  |  |  | 1. check the category is displaying or not | 1. report category should not be shown after ordering a product | 1. report category isnt showing | pass
[5 empty] | 1. check the category is displaying or not, while not having a pending order / cancelled order | 1. category should not be displayed | 1. category not displayed | pass
profile_020 |  |  |  |  | 1. write on the ''report title'' text box and check if its working perfectly | text box should work fine | text box worked fine | pass
profile_021 |  |  |  |  | 1. write on report issue in details section, and check if the text box is being written | text box should work fine | text box worked fine | pass
profile_022 |  |  |  |  | 1. check the text box resizing option is resizing the text box | resizing option should resize the text box | resizing is working perfectly | pass
profile_023 |  |  |  |  | 1. resize the text box to smallest possible and check if the quality of text is good | 1. the quality of texts should be high | 1. the quality of the texts are decreased after smalling the text box of lenght ''3px'' | fail | 3
profile_024 |  |  |  | write sentence and check if the sentence meets the area and automatically broads the text area | 1. write anything that fills the text box area (height & width) and check if the box broads automatically | 1. area should automatically broad | 1. area broaden | pass
profile_025 |  |  |  |  | 1. check the charecter quality | 1. quality should be high | 1. quality isnt high | fail | 4
profile_026 |  |  |  | try to submit issue with different cases | 1. try to submit with all the empty text boxex | 1. should not accept submission | 1. submission is not accepting | pass
profile_027 |  |  |  |  | 1. select category only and check if the submission is accepting | 1. should not accept submission | 1. submission is not accepting | pass
profile_028 |  |  |  |  | 1. only wirte down the title and check if the submission is accepting | 1. should not accept submission | 1. submission is not accepting | pass
profile_029 |  |  |  |  | 1. only write down the details of issue and check if the submission is accepting | 1. should not accept submission | 1. submission is not accepting | pass
profile_030 |  |  |  |  | 1. fill all the boxex with valid information while placed order | 1. should accept submission | 1. submission is not accepting | pass
[5 empty] | 1. fill all the boxes with valid information while not placing order or cancelled order | 1. should not accept submission | 1. submission didnt accepted | pass
profile_031 |  |  | click on ''profile'' and check all the functionalities | check previously inputed data is stored in the form | 1. check the profile picture | 1. profile picture should change | 1. profile picture isnt changing
profile_032 |  |  |  |  | 1. check the name | 1. name should change | 1. name isnt changing
profile_033 |  |  |  |  | 1. check the number | 1. number should change | 1. number is changed
profile_034 |  |  |  |  | 1. check the gender check box | 1. gender check box should change | 1. checkbox is changed
profile_035 |  |  |  | check the form field with various cases | 1. leave all the boxes empty and try to submit | should not submit
profile_036 |  |  |  |  | 1. fill the name and leave the rest of the boxes empty | should not submit
profile_037 |  |  |  |  | 1. fill only number and leave all the boxes empty | should not submit
profile_038 |  |  |  |  | 1. fill the boxes with valid informations | should be submit
profile_039 |  |  |  | check if we change the information then is it changing or not | 1. check if the profile picture is changing | 1. profile picture should change | 1. profile pircture didnt change | fail | 5
profile_040 |  |  |  |  | 1. check if the name is changed after changing the name | 1. name should change | 1. name didnt change | fail | 6
profile_041 |  |  |  |  | 1. check if the number is changed after changing the name | 1. number should change | 1. number changed | pass
profile_042 |  |  |  |  | 1. check if the check box changed | 1. check box details should change | 1. checkbox details changed | pass
profile_043 |  |  | 1. click logout 2. check the logout function | click log out and check wether the current ID is loging out successfully | 1. check if the current ID is logging out successfully | 1. should log out | 1. successfully logged out | pass
profile_044 |  |  |  | after logging out check if the page redirect to the home page without the ID and ''sign in'' messege appears on the right corner of the navbar | 1. after loging out check if sign in messege appears | 1. should appeaer a sign in messege | 1. sign in messege appeared | pass

## search products
test ID | precondition | steps to execute | test case comments | test case title | expected result | actual result | status | test data | comments | bug_ID
| load the homepage https://evaly.com.bd/ | 1. load the page https://evaly.com.bd/ 2. click on search option 3. search any product |  | check the search box
search_p_001 |  |  |  | check the trending product & search is displayed | 1. trending products & search should display | trending products & search is displayed | pass
search_p_002 |  |  |  | search a particular product & check that searched products are all same catagory | 1. searched products should be same catagory and the product keywords | 1. search products are same category & same as the keyword given | pass
search_p_003 |  |  |  | 1. search two products in a row | 1. if the keyword matches the product keyword or description, then it will show otherwise it will take first word as keyword | 1. product displayed if the keyword matches 2. took the first word as keyword | pass
search_p_004 |  |  |  | 1. check if the search option catches the word mispelling | 1. couldnt detect mispelling (Its not a bug rather than a AI controlled system) | 1. didnt detect mispelling | fail |  |  | 1
search_p_005 |  |  |  | 1. verify that, if i write something in search option then suggestions should display beneath the search box | 1. suggestions should appear according to the alphabets the client writes | 1. suggestion appeared | pass
search_p_006 |  |  |  | 1. leave the search box empty and click search | 1. all categories of products should appear | 1. all categories of product is appeared | pass
check the product filter
search_p_007 |  |  |  | 1. select a category and check if all the products belong to the selected category | 1. all product should belong to selected category | 1. all product belongs to the selected category | pass
search_p_008 |  |  |  | 1. select a brand only, and check if all the products belong to the selected brand | 1. all product should belong to selected brand | 1. all product belong to selected brand | pass
search_p_009 |  |  |  | 1. select a catergory and brand to verify that products are from that category and brand | 1. all product should belong to selected category and brand | 1. all product belonged to the selected category and brand at the same time | pass
search_p_010 |  |  |  | 1. select a brand, if the brand doesnt contain any product then in the category it wont show the product | 1. after selecting a brand, if the brand doesnt contain any category then it should not display | 1. category is not displayed | pass
search_p_011 |  |  |  | 1. select a category, if any brand doesnt contain the product then the brand name wont show | 1. the brand name should not be displayed | 1. brand is not displayed | pass
select all the category & select a brand and see if the selected category has an effect
search_p_012 |  |  |  | 1. select multiple product category and select a brand | 1. selected categories and brand should be same 2. all products should belong to the selected category and brand | 1. categories and brand are same 2. all products belong to the selected category and brand | pass
search_p_013 |  |  |  | 1. check if the reset button works | 1. reset button should reset all the selected category | 1. reset button works | pass
search_p_014 |  |  |  | 1. select all the category and select each brand. Check if the category is selected / behaving expected | 1. category should be selected if the product is available otherwise no | 1. category is not selected after choosing a brand though it has the product | fail |  |  | 2
check the sort button
search_p_015 |  |  |  | 1. donot select the sort option | 1. products should be randomly displayed | 1. products are randomly displayed | pass
search_p_016 |  |  |  | 1. select sort from lowest to highest | 1. products should be displayed from lowest price range to highest price range | 1. products are displayed from the lowest price to highest | pass
search_p_017 |  |  |  | 1. select sort from highest to lowest | 1. products should be displayed from highest price range to lowest price range | 1. products are displayed from highest to lowest price | pass
|  | 1. load home page 2. go to category 3. select a category |  | search products via category
search_p_018 |  |  |  | 1. select a category & check if the right category is displayed | 1. displayed products should belong to selected category | 1. selected product belongs to selected category | pass
visual appearence
search_p_019 |  | 1. go to category navigation 2. select a category and check the followings |  | 1. after selecting a category, verify that if the products categories headline is displayed correctly, otherwise it might be difficult to find out the category | The headline of category should display in headline | 1. headline is not displayed but it displays the products of that category 2. headline is 30-35 px above from a proper visualization | fail | 1. category : for all categories |  | 3
search_p_020 |  |  |  | 1. after selecting a category, select a product then get back to category page. check if the category page redirect to the first category page | 1. product page should redirect to the category page | 1. product redirected to the back page | pass |  | 1. we have to click back button 2 times to go back to the category page | 4
|  |  | if we click the sort button continuosly then try to return to the back page it wont go back. after the same amount of back click needed that we clicked to the sorting button - it means how many times we click on sort button it creates a new page. Then if we try to go back it is going through all the pages that we have created | if we click the sort button continuosly then try to return to the back page | 1. should not create a new page 2. if we click on back button it should immediately return to the back page | 1. created a new page 2. after clicking back button it didnt go back to the page that we came from instead of going through the created pages | fail
check the product availablity. Product should display after selecting a category.
search_p_021 |  |  |  | 1. select a product from category and check if the product is available | 1. all products should be available | 1. some products are unavailable | fail |  | 1. all the products are not available the data base might not contain the data or there is a malfunctioning. Though im giving this test case as failed | 5
search_p_022 |  |  |  | 1. check if the product is selected in the category section on the left side of the display | 1. after selecting a product new page is displayed showing the products. So in the left side of the page product should be selected | 1. product is selected | pass

## login_bug
bug ID | precondition | step to bug | bug description | expected result | actual result | priority | enviornment | attatch ments
lg_1 | load the signup page | 1. go to signup page 2. try to login with unregistered email account | when we enter the unregistered email we do not get any caution messege. login page requires a OTP after giving a unregistered email | 1. should not send OTP to an unregistered email 2. should be able to find out the unregistered email and show messege | 1. OTP send to a unregistered email 2. didnt find out the unregistered email and didnt show any messege about the email | high | windows
lg_2 | load the login page | 1. go to the login page 2. enter email 3. click forgot password | 1. after entering a email that has not signed up by evaly account forms do not send otp when we change the password, hence it should send an OTP as one time password to login | should send OTP to evaly accounts. It sends OTP to only directly signed up google accounts | didnt send OTP | high | windows
lg_3 | load the login page | 1. go to login page 2. enter password 3. click the hide/unhide button for password | in password section, The hide button unhide the password, unhide button hides the password | hide button should hide the password, unhide button should unhide the password | hide button unhide the password unhide button hides the password | high | windows

## cart bug
bug ID | precondition | step to bug | bug description | expected result | acutal result | status | priority | attatchments
1 | load the dash board 2. select the address navigation | 1. go to dashboad board 2. select ''delivery address'' in navigation | if we select the ''outside town'' check box and give inside town information then system should figureout that this is not outside town address. - system should not continue submission - the union form in empty. login continued with empty UNION. Rather that system should find out the false address | - address submission should not continue | - address submission continued | fail | high
[9 empty] | before loggin out we added a product to the cart | after log out and again login to another ID
2 | load the cart | 1. add product to the cart 2. log out and login to another ID | - if we add a product to the cart and log in to another ID with same product the product still exists. | - the added product should be reset while loggin out | - added product didnt reseted with new ID | fail | high

## profile_bug
bug ID | precondition | steps to bug | bug description | expected result | actual result | priority | attatchments
1 | load the ''order'' navigation | 1. go to homepage 2. click on order navigation 3. click on a order details | in the previous order details the clients profile picture is set to default but it should show the clients accounts picture | should show the clients accounts picture | default profile picture is displayed | high
2 |  |  | when we cancel the order, the cancellation time is accordint to the computer of the client but it should show the international time in the cancellation time | should show the international time because computer time could be wrong sometimes | displaying local time | high
3 |  |  | in the resize box, if we resize the box to a particular size then the text loses quality | resize box should contain a qualitiful texts after resizing the box | text quality loses after resiziing the text box of ''details text box'' | medium | after resizing |  | before resizing
4 |  |  | in the text box if we write any sentences and after meeting the max height and width it automatically broads but after that the text quality decreases | text quality should be high | text quality decreased | medium | before meets the max height and width | after meets the max height and width
5 |  |  | in the profile picture section if we try to change profile picture then all information saved messege appears but profile picture is not changing | profile picture should change | profile picture didnt change | high | this is shown in profile picture seciton after changing the profile picture
6 |  |  | after changing the name in profile, the name is not changed. the name is displaying the google accounts name / first time sign in inputed name | should change the profile name | didnt change the profile name

## search products_bug
bug ID | precondition | steps to bug | bug descriiption | expected result | actual result | priority | attatchments
1 | 1. come to dashboard 2. search products | 1. go to dashboard 2. search any product with mispelling | when we try to search product with mispelling it doesnot show the product with automatically correction word. basically it is a common and user friendly feature | should automatically correct the word and find the right product | didnt automaticallly correct and couldnt find the product if the spelling doesnt match | medium
searched ''sheo'' instead of ''shoe'' and it couldnt respell
2 | search product and see the category and brand section | 1. select all the category 2. beneath the category- select a brand | basically after chosing a brand some category is unselected. It should be unselected if there is no such brands product available. but there are products available | 1. category should be selected after chosing a brand if there is such product that belong to that brand | 1. in some cases category become unselected though it has the product which belong to the brand | high
[7 empty] | selected all category but not the brand | after selecting a brand
3 | 1. come to dashboard 2. click on category navigation | 1. click on category navigation 2. select a category above | after clicking the category the products lists comes according to the category that has been selected. But the headling of the listing is some pixel above from where it should be. It should be in customers eye sight | headline should be in clients eye sight and visible | headline is not visible headline is some pixels above from where it should be | high
4 | 1. load a product page | 1. select any product 2. go to product page 3. click on price sorting button | if we click the sort button continuosly then try to return to the back page it wont go back. after the same amount of back click needed that we clicked to the sorting button - it means how many times we click on sort button it creates a new page. Then if we try to go back it is going through all the pages that we have created | should retuen to the back page immedietely after clicking the back button. | didnt go back after clicking the back button instead of that - it back to the created new page that has been created at every time we click the price sorting button | high
5 | load a product page | 1. select a product 2. check the product quantity | sometimes if we click the product that it wont show any products avialable where all products should be available. If not then at least a messege should be appear in the product display so that client do not have to click the product to check if that product is available | 1. should contain all product 2. or should display product unavailablity | 1. not all products are available 2. not showing product unavailablity in product display | low